## 1. Product Overview
Item | Description
Product Name | GateCompass
Product Vision/ Purpose | Improve Preparation Experience of GATE aspirants
Business Goals / Key Success factors | maximze the number of downloads for our applications
Primary Stakeholders | GATE aspirants

## 2. Product Backlog
Product Backlog
Epic ID | Epic Title | User Story ID | User Story/Requirement | Technical Requirements | Priority (MoSCoW) | Story Points | Status | Owner | Test Case (Tasks) | Test Owner
E1 | Predictive Topic Importance | US1 | As a user, I want ML-based forecasting of important topics for GATE exam | Python Flask ML service, scikit-learn | Must Have | 13 | Done | ML Team | Predictions are accurate
E2 | Continuous Learning | US2 | As a user, I want automated updates and retraining of the system | Node-cron scheduled tasks | Should Have | 5 | Done | Backend Team | Tasks run on schedule
E3 | Historical Trend Analysis | US3 | As a user, I want to see historical trend analysis of past GATE paper patterns | Chart.js & Recharts integration | Must Have | 8 | Done | Frontend Team | Charts render correctly | Mallamma
E4 | Balanced Mock Tests | US4 | As a user, I want balanced mock tests with calibrated difficulty | Node.js test generator | Must Have | 13 | Done | Backend Team | Tests generate properly | Himanshu &Nihar
E5 | Performance Analytics | US5 | As a user, I want detailed performance analytics with radar charts and heatmaps | Chart.js visualization | Must Have | 8 | Done | Frontend Team | Analytics display correctly | Anushka & Ankana
E6 | PWA Support | US6 | As a user, I want offline mock test capability | PWA implementation | Should Have | 8 | Done | Frontend Team | Works offline
E7 | Dark Mode | US7 | As a user, I want dark mode for eye-friendly interface | Material-UI dark theme | Could Have | 3 | Done | Frontend Team | Theme switches properly | Nihar
E8 | Source Code Management | US8 | As a user, I want access to source code and documentation | GitHub repository setup | Must Have | 5 | Done | Full Stack Team | Code compiles and runs | Mohit.Ganolia
Notes:
Category | Description
MoSCoW - Must Have | Critical requirements that are essential for the project's success and must be delivered.
MoSCoW - Should Have | Important requirements that are highly desirable but not vital; the project can still be delivered without them, but it would be less ideal.
MoSCoW - Could Have | "Nice-to-have" requirements that are less important and have a lower impact if they are not included.
MoSCoW - Won't Have | Requirements that are not being delivered in the current project or timeframe, but may be considered for future iterations.
Story Points - Fibonacci (Modified) | 0, 1, 1, 2, 3, 5, 8, 13, 20 (points decided based on a User Story's complexity, effort needed & risks). Ends at 20. Rarely extended to 40 and 100 for very large tasks.

## 3. Roadmap
Release | Target Date | Key Features | Dependencies | Demo Status
v0.1 | 2025-12-25 | Predictive Topic Importance | ML Service | Done
v0.2 | 2025-11-22 | Historical Trend Analysis | Chart.js | Done
v0.3 | 2025-12-29 | Balanced Mock Tests | Backend API | Done
v0.4 | 2025-12-06 | Performance Analytics | User Data | Done
v0.5 | 2025-12-25 | Continuous Learning | Cron Jobs | Done
v0.6 | 2025-12-20 | Dark Mode | Frontend Libs | Done
v1.0 | 2025-01-01 | Complete Platform Launch | All Epics | Done

## 4. Retrospective
Note: This is for the team to learn and improve. I have taught you in the class on Nov 4, 2025.
Ideally, the team should do this at the end of every release. How often you do, I leave it to you.
What Went Well | What Went Well | Improvements / Action Items (Next time what will you do differently) | Owner
Team collaboration was great | Test coverage was low | Automate test pipeline in next sprint | Test Lead
Predictive topic importance feature working well | ML model training time | Optimize ML algorithms | ML Team
Historical trend analysis implemented successfully | Chart rendering delays on mobile | Optimize charts for mobile | Frontend Team
Mock test generation working perfectly | Database scaling concerns | Implement database monitoring | Backend Team
Performance analytics providing valuable insights | Data processing speed issues | Optimize analytics algorithms | Frontend Team
PWA implementation successful | Offline storage limits | Increase PWA storage capacity | Frontend Team
Dark mode well received by users | Theme switching bugs | Fix dark/light mode transition | Frontend Team
Source code documentation completed | Code review process slow | Streamline code review process | Full Stack Team